

**Action plan and Roadmap to the 13th CAADP PP Meeting**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Action Area** | **Lead** | **Milestone** | **July 2016** | **January 2017** | **Next PP** |
| 1. AUC, NPCA and the RECs to lead the design a comprehensive Malabo financing architecture with a Continental, Regional and National perspective.    1. Accelerated implementation,    2. Coordination,    3. Complementarity and    4. Accountable partnership across Africa. | Core Team |  |  |  |  |
| 1. Finance Landscape and Policy Environment: Member States and Development Partners highlight ways in which development finance can be delivered to the grassroots in an efficient and cost effective manner.    1. Assess and map policy environment in selected countries.    2. Support dialogue between the public sector, private sector and non-governmental organisations.    3. Support components for women and youth addressing land ownership and nutrition sensitive agriculture.    4. Support smart investment opportunities for the youth based on quick returns, technology and innovation.    5. Leverage and align with CTA and AFRACA efforts. | Core Team  Erick Sile  Erick Sile  Abraham Sarfo  Abraham Sarfo  Augustin Wambo Yamdjeu | Investment Facilitation Platform (IFP)  IFP  NEPAD Youth Initiatives  NEPAD Youth Initiatives  Agreement and Action plan |  |  |  |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Action Area** | | **Lead** | **Milestone** | | **July 2016** | **January 2017** | **Next PP** |
| 1. Support the definition and dissemination innovative finance frameworks for adoption to ensure accelerated implementation of identified priorities in RAFSIPs and NAFSIPs. | | Core Team | Policy support | |  |  |  |
| 1. Support the Private Sector to translate Malabo commitment into viable business plans that can attract required resources necessary for accelerated implementation. | | Core Team | Confirmation of linkage into RAFSIPs and NAFSIPs. | |  |  |  |
| 1. On Innovative Delivery of Financial Services: Support policy environment for the digital financial services and data management. | | Erick Sile | Policy support | |  |  |  |
| 1. On Value Chain Finance: Support smallholder farmers and the small and medium enterprises (SMEs) on how to conduct business and improve business skills and market access.    1. Linked to the digital financial services initiative under Point 5. | | Core Team | Policy support under Point 5 | |  |  |  |
| 1. On Agriculture and Food Insecurity Risk Management: Support the improvement of the following:    1. Regulatory framework for risk management    2. Information systems.    3. Capacity development.    4. Development of Public Private Partnerships | | Mariam Sow | Country Assessment Reports | |  |  |  |
| 1. On Renewing Partnership for Accelerated Development.    1. Jointly develop a partnership paper with contributions from all parties involved.    2. Addressing financial sustainability.    3. Alternative funding models aligned to the level of development. | | Core Team | Proposal for the new partnership | |  |  |  |
| **Action Area** | **Lead** | | **Milestone** | **July 2016** | **January 2017** | **Next PP** | |
| 1. Member states to disseminate and sensitise stakeholders and local communities the messages around Malabo with support of RECs, AUC and NPCA. | Core Team | | Confirmation of method and content |  |  |  | |
| 1. Facilitate the conduct of the RAFSIP/NAFSIP appraisals and establishment of the continental Biennial Review Mechanism informed by national accountability frameworks. | Core Team | | Appraisal reports |  |  |  | |
| 1. Facilitate technical support for implementation of New Generation of NAFSIPs through the establishment of Technical Networks. Technical Networks will help identify appropriate policies, programs and practices that can accelerate achievement of the Malabo Declaration goals and targets. | Core Team | | Commitment of support |  |  |  | |
| 1. Give an update on the NAFSIPs Appraisal, the establishment of the Technical Networks in the 13th CAADP PP. | AUC Team | | Progress report on the establishment of the Technical committees by AUC |  |  |  | |
| 1. RECs and Member States to build synergy and coherence of appraised NAFSIP and RAFSIP to ensure coordination within and across economic communities. | Core Team | | Reports |  |  |  | |

| **Action Area** | **Lead** | **Milestone** | **July 2016** | **January 2017** | **Next PP** |
| --- | --- | --- | --- | --- | --- |
| 1. Parliamentarians at continental, country and regional level to support the implementation of Malabo declaration through legislation, budget planning process, policy, oversight and as well as advocacy for the agricultural sector.    1. Create awareness among the parliamentary committees on agriculture and finance.    2. Create a basic agricultural policy course module tailored for parliamentarians.    3. Implement the policy course in selected country parliamentary committees on agriculture and finance. | Core Team | Agricultural policy course content and delivery programme |  |  |  |
| 1. AUC and NPCA and all actors should report on progress in implementation of PP actions. | Core Team | Progress reports |  |  |  |